## <date>
Project status report
Update the status and priority fields using the drop-down menus | [5 empty] | BETTER THAN PLANNED
Project name |  |  | Project manager |  |  | ON TRACK
Overall status | AT RISK |  |  |  |  | AT RISK
Schedule | BETTER THAN PLANNED | Budget | ON TRACK | Scope / quality | IN JEOPARDY | IN JEOPARDY
Work completed since the last report |  |  | Work to be completed by the next report
EXCEPTIONS | [5 empty] | CRITICAL
Risk / issue | [5 empty] | SERIOUS
Owner |  | Date first reported |  | Priority | MODERATE | MODERATE
Schedule impact | Budget impact | Scope / quality impact | Other impacts | Actions in place | Actions required | LOW
Risk / issue
Owner |  | Date first reported |  | Priority | LOW
Schedule impact | Budget impact | Scope / quality impact | Other impacts | Actions in place | Actions required
Copy and paste here any additional exceptions as required
LESSONS LEARNED | [5 empty] | CRITICAL
Copy a new sheet for each status update and label it by date
Update the drop-down menu fields in (hidden) column G
This project management template is provided free of charge by the Center for Project Innovation under a GNU General Public License.
By downloading and using this resource, you accept its terms and conditions of use.
In short, you can redistribute and/or modify this template to your heart’s content, but without any warranty (real or implied) about its merchantability or fitness for a particular purpose.
This template is offered ‘as is’, and is not supported by a help desk. Please visit https://microsoft.com for editing tips and tricks.
For example, the excel sheets are protected to prevent accidentally overwriting formulas, but not password protected.
You can contact us to learn how this or other project management assets might be customised for your project or organisation.
This template is provided free of charge by the Center for Project Innovation under a GNU General Public License.
By downloading and using this resource, you accept its terms and conditions of use.
In short, you can redistribute and/or modify this template to your heart’s content, but without any warranty (real or implied) about its merchantability or fitness for a particular purpose.
This template is offered ‘as is', and is not supported by a help desk. Please visit http://microsoft.com for editing tips and tricks.
Make sure you remember to delete the <blue guidance text> before submitting it for approval!
You can contact us to learn how this or other project management assets might be customized for your project or organization.

## Example
Project status report
Update the status and priority fields using the drop-down menus | [5 empty] | BETTER THAN PLANNED
Project name | XYZ Project |  | Project manager | Alex |  | ON TRACK
Overall status | AT RISK |  |  |  |  | AT RISK
Schedule | BETTER THAN PLANNED | Budget | IN JEOPARDY | Scope / quality | ON TRACK | IN JEOPARDY
| We are ahead of schedule due to some key tasks taking less time than expected |  | Getting the tasks completed on time meant hiring more contractors, exceeding the budget |  | The work in progress has been inspected by the client and meets their expectations
Work completed since the last report |  |  | Work to be completed by the next report
We have completed the Phase 1 tasks by the due date and commenced ahead of schedule some of the Phase 2 tasks |  |  | We are on track to finish the phase 2 tasks one week ahead of schedule, although bad weather is forecast which may delay us slightly
EXCEPTIONS | [5 empty] | CRITICAL
Risk / issue | Bad weather forecast |  |  |  |  | SERIOUS
Owner | Alex | Date first reported | Today | Priority | LOW | MODERATE
Schedule impact | Budget impact | Scope / quality impact | Other impacts | Actions in place | Actions required | LOW
May cause delay | None | None | None | Reserve days available given we are ahead of schedule at this point | Continue monitoring the situation
Risk / issue | Key staff may be reallocated to other projects given we are ahead of schedule
Owner | Alex | Date first reported | Today | Priority | MODERATE
Schedule impact | Budget impact | Scope / quality impact | Other impacts | Actions in place | Actions required
May cause delay | May save money | Need to guarantee work is continnued at a high standard | Client expectations should be managed | Only reallocate if weather forecast to be fine - client still very driven by on-time delivery as their most important success criterion | Preauthorise change request reassigning staff to be delivered once weather risk is retired
Copy and paste here any additional exceptions as required
LESSONS LEARNED | [5 empty] | CRITICAL
Using subcontractors at greater expense to get ahead of schedule may not be worth the budget hit if not requested by the client
Copy a new sheet for each status update and label it by date
Update the drop-down menu fields in (hidden) column G
This project management template is provided free of charge by the Center for Project Innovation under a GNU General Public License.
By downloading and using this resource, you accept its terms and conditions of use.
In short, you can redistribute and/or modify this template to your heart’s content, but without any warranty (real or implied) about its merchantability or fitness for a particular purpose.
This template is offered ‘as is’, and is not supported by a help desk. Please visit https://microsoft.com for editing tips and tricks.
For example, the excel sheets are protected to prevent accidentally overwriting formulas, but not password protected.
You can contact us to learn how this or other project management assets might be customised for your project or organisation.
This template is provided free of charge by the Center for Project Innovation under a GNU General Public License.
By downloading and using this resource, you accept its terms and conditions of use.
In short, you can redistribute and/or modify this template to your heart’s content, but without any warranty (real or implied) about its merchantability or fitness for a particular purpose.
This template is offered ‘as is', and is not supported by a help desk. Please visit http://microsoft.com for editing tips and tricks.
Make sure you remember to delete the <blue guidance text> before submitting it for approval!
You can contact us to learn how this or other project management assets might be customized for your project or organization.